## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 50
| Number of testers | 1
| Test cycle duration | 5 days
Status for
| Number of test cases planned | 50 | The gap in the total executed and planned can be absorbed by the QA team
| Number of test cases executed | 50
| Number of test cases executed overall | 50
| Number of defects encountered today | 2
| Number of defect encountered so far | 10
| Number of critical defects- still open | 3
Overall status
| Number of test cases planned | 50
| Number of test cases executed | 50
| Pass Percentage of the defects | 98%
| Defects density | 1
| Critical defects percentage | 50%

## Detailed status
Module | Scenarios | Sub Levels | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
1 | Authentication | User Registration | Valid email & password | Low | Amit M | 5/15/2026 | Pass | - | -
2 | Authentication | User Registration | Invalid email format | Low | Amit M | 5/15/2026 | Pass | - | -
3 | Authentication | User Registration | Password <12 characters | Low | Amit M | 5/15/2026 | Pass | - | -
4 | Authentication | User Registration | Duplicate email submission | Low | Amit M | 5/15/2026 | Fail | DEF-001: Duplicate email not rejected | High
5 | Authentication | User Login | Valid credentials | Low | Amit M | 5/15/2026 | Pass | - | -
6 | Authentication | User Login | Invalid password | Low | Amit M | 5/15/2026 | Pass | - | -
7 | Authentication | User Login | Account lockout after 5 attempts | Medium | Amit M | 5/16/2026 | Pass | - | -
8 | Authentication | JWT Validation | Valid token access | Low | Sarah K | 5/16/2026 | Pass | - | -
9 | Authentication | JWT Validation | Expired token rejected | Low | Sarah K | 5/16/2026 | Fail | DEF-002: Expired token validation failed | High
10 | Authentication | JWT Validation | Invalid token format | Low | Sarah K | 5/16/2026 | Pass | - | -
11 | Artist Upload | Track Upload | Valid MP3 file upload | Medium | Priya S | 5/17/2026 | Pass | - | -
12 | Artist Upload | Track Upload | File size exceeds 500MB | Medium | Priya S | 5/17/2026 | Pass | - | -
13 | Artist Upload | Track Upload | Invalid audio format rejected | Medium | Priya S | 5/17/2026 | Pass | - | -
14 | Artist Upload | Metadata Entry | Valid metadata submitted | Low | Priya S | 5/17/2026 | Pass | - | -
15 | Artist Upload | Metadata Entry | Price below $0.99 rejected | Low | Priya S | 5/17/2026 | Pass | - | -
16 | Artist Upload | Metadata Entry | Price exceeds $99.99 rejected | Low | Priya S | 5/17/2026 | Pass | - | -
17 | Artist Upload | Preview Generation | 30-second preview generated | Medium | Priya S | 5/17/2026 | Fail | DEF-003: Preview generation timeout error | High
18 | Artist Upload | Duplicate Check | Duplicate upload prevented | Medium | Priya S | 5/18/2026 | Pass | - | -
19 | Artist Upload | Track Status | Track shows "Pending" state | Low | Priya S | 5/18/2026 | Pass | - | -
20 | Artist Upload | Upload Confirmation | Email notification sent | Low | Priya S | 5/18/2026 | Pass | - | -
21 | Marketplace Search | Search by Keyword | Results found for query | Low | Raj P | 5/18/2026 | Pass | - | -
22 | Marketplace Search | Search by Keyword | Empty results handled | Low | Raj P | 5/18/2026 | Pass | - | -
23 | Marketplace Search | Filter by Genre | Genre filter functionality | Low | Raj P | 5/18/2026 | Pass | - | -
24 | Marketplace Search | Filter by Mood | Mood filter functionality | Low | Raj P | 5/18/2026 | Pass | - | -
25 | Marketplace Search | Sort by Price | Ascending price sort | Medium | Raj P | 5/19/2026 | Pass | - | -
26 | Marketplace Search | Sort by Popularity | Popularity ranking sort | Medium | Raj P | 5/19/2026 | Blocked | DEF-004: Popularity calculation incomplete | Medium
27 | Marketplace Search | Pagination | 20 results per page | Low | Raj P | 5/19/2026 | Pass | - | -
28 | Marketplace Search | Cache Performance | Response time <500ms | Medium | Raj P | 5/19/2026 | Pass | - | -
29 | Purchase Process | Add to Cart | Track added successfully | Low | Lisa M | 5/20/2026 | Pass | - | -
30 | Purchase Process | Checkout | Order summary displayed | Low | Lisa M | 5/20/2026 | Pass | - | -
31 | Purchase Process | Payment Processing | Valid payment accepted | High | Lisa M | 5/20/2026 | Pass | - | -
32 | Purchase Process | Revenue Split | Artist receives 90% | High | Lisa M | 5/20/2026 | Pass | - | -
33 | Purchase Process | Revenue Split | Platform receives 10% | High | Lisa M | 5/20/2026 | Pass | - | -
34 | Purchase Process | Wallet Update | Artist wallet balance updated | High | Lisa M | 5/21/2026 | Pass | - | -
35 | Purchase Process | Wallet Update | Platform wallet balance updated | High | Lisa M | 5/21/2026 | Pass | - | -
36 | Purchase Process | Transaction Atomicity | All-or-nothing transaction | High | Lisa M | 5/21/2026 | Pass | - | -
37 | Purchase Process | Download Access | Fan receives download link | Low | Lisa M | 5/21/2026 | Pass | - | -
38 | Purchase Process | Purchase Confirmation | Confirmation email sent | Low | Lisa M | 5/21/2026 | Pass | - | -
39 | Streaming | Preview Playback | 30-second preview plays | Low | John D | 5/22/2026 | Pass | - | -
40 | Streaming | Full Audio Playback | Full track audio streams | Medium | John D | 5/22/2026 | Pass | - | -
41 | Streaming | Buffer Time | Playback starts within 5 seconds | Medium | John D | 5/22/2026 | Fail | DEF-005: Audio buffering exceeds 5 seconds | High
42 | Streaming | Access Control | Non-purchased users blocked | High | John D | 5/22/2026 | Pass | - | -
43 | Admin Approval | Queue Display | Pending tracks displayed | Low | Admin-1 | 5/23/2026 | Pass | - | -
44 | Admin Approval | Track Preview | Admin preview functionality | Low | Admin-1 | 5/23/2026 | Pass | - | -
45 | Admin Approval | Approve Track | Track status changed to approved | Medium | Admin-1 | 5/23/2026 | Pass | - | -
46 | Admin Approval | Reject Track | Rejection reason stored | Medium | Admin-1 | 5/23/2026 | Pass | - | -
47 | Admin Approval | Artist Notification | Artist notified of decision | Low | Admin-1 | 5/23/2026 | Pass | - | -
48 | Admin Approval | SLA Compliance | 48-hour SLA enforced | High | Admin-1 | 5/24/2026 | Blocked | DEF-006: SLA timer calculation error | High
49 | Earnings Dashboard | View Earnings | Cumulative earnings displayed | Low | Priya S | 5/24/2026 | Pass | - | -
50 | Performance | Load Testing | 2000 concurrent users supported | High | Performance Team | 5/25/2026 | Pass | - | -

## Bug report
Defect ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
Defect ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
DEF-001 | Duplicate email not rejected during registration | 1. Navigate to Registration page. 2. Register with email test@example.com. 3. Attempt to register again with the same email. | High | New | Amit M | Lead Dev
DEF-002 | Expired JWT token validation failed | 1. Generate a JWT with a short expiration. 2. Wait for token to expire. 3. Attempt to access a protected route using the expired token. | High | New | Amit M | Security Dev
DEF-003 | Preview generation timeout error | 1. Log in as Artist. 2. Upload a valid audio file (e.g., 100MB MP3). 3. Trigger "Generate Preview" and observe the system timeout. | High | New | Amit M | Backend Dev
DEF-004 | Popularity calculation logic incomplete | 1. Navigate to Marketplace. 2. Apply "Sort by Popularity" filter. 3. Observe null/incorrect sorting order. | Medium | New | Amit M | Data Engineer
DEF-005 | Audio buffering exceeds 5 seconds | 1. Navigate to a track page. 2. Click Play on the full track. 3. Measure time from "Click" to "Audio Start" under standard 4G/Broadband. | High | New | Amit M | Streaming Dev
DEF-006 | SLA timer calculation error (48-hour enforcement) | 1. Upload a track to the Admin queue. 2. Monitor the SLA countdown timer. 3. Observe calculation discrepancies vs. actual wall-clock time. | High | New | Amit M | Backend Dev